# STIMU MANDALAY
SEPTEMBER OPEN HOUSE 2026

Student Conversion Playbook

Core proposition: One STIMU • Student-to-Student Trust • Parent Confidence • October Conversion

# 1. One flagship STIMU MDY Future Experience Open House in mid-September as a focused October-intake conversion intervention—not a general promotional event. အဓိကရည်ရွယ်ချက်မှာ event attendance မဟုတ်ဘဲ qualified prospects များကို application နှင့် registration အဖြစ် ပြောင်းလဲရန် ဖြစ်သည်။

| Board KPI | Target / Approval Benchmark |
| --- | --- |
| Prospective students | 80–100 |
| Parents / family decision-makers | 40–60 |
| YGN Student Ambassadors | 15–20 |
| MDY Student Ambassadors | 8–12 |
| Qualified prospects | 60+ |
| Applications within 72 hours | 30+ |
| Event-attributable registrations | 15–20 |

# 2. Strategic Rationale | ဘာကြောင့် ဒီ Event ကိုလုပ်သင့်သလဲ

• MDY prospects should experience STIMU through real students, not only through management presentations. YGN students create aspiration and demonstrate the scale of the wider STIMU community; MDY students provide local credibility and relatability.

• Parents need confidence in institutional credibility, academic quality, student care, career outcomes and value. Senior management and faculty must therefore be visible and accessible.

• The event should communicate: “MDY is part of One STIMU.”  MDY campus ကို secondary campus အဖြစ် မခံစားစေဘဲ Yangon–Mandalay student community တစ်ခုတည်းဖြစ်ကြောင်း လက်တွေ့ပြသရန်။

# 3. Event Concept & Psychology

| Audience Psychology | Event Response |
| --- | --- |
| Student: “Will I fit in? Is STIMU modern and worth choosing?” | Peer conversations, YGN + MDY student stories, program experiences, belonging. |
| Parent: “Can I trust STIMU and is this investment worthwhile?” | Management access, faculty consultation, career pathways, fees/scholarship clarity. |
| MDY concern: “Is Mandalay less important than Yangon?” | Visible YGN participation + One STIMU message + shared student community. |
| Decision barrier: “I’m interested, but not ready.” | Family consultation + eligibility check + immediate Apply/Join pathway. |

# 4. Signature Conversion Mechanism — Ask a STIMU Student

Format: 5–8 prospects + 2 YGN students + 1 MDY student per small group. Management should not dominate these conversations. Prospects can openly ask about lecturers, workload, student life, opportunities, Yangon–Mandalay connection and whether current students would choose STIMU again.

Ambassador selection rule: Choose confident, friendly and authentic students across programs—not only top academic performers. Where possible, include YGN students with Upper Myanmar backgrounds.

# 5. Recommended 3–4 Hour Event Flow

| Time | Activity | Conversion Purpose |
| --- | --- | --- |
| 09:00–09:30 | Welcome, refreshments, informal student mingling | Reduce barriers / belonging |
| 09:30–09:45 | Senior Management Welcome | Parent trust + One STIMU |
| 09:45–10:00 | YGN + MDY student stories | Social proof |
| 10:00–10:45 | Ask a STIMU Student circles | Core peer conversion |
| 10:45–11:20 | Program Experience Zones | Create program desire |
| 11:20–11:40 | Career & degree pathway | Outcome confidence |
| 11:40–12:10 | Parent session / student networking | Resolve objections |
| 12:10–13:00 | Family consultation → Apply → Join | Close |

# 6. Experience Zones — Keep It Simple

| Zone | What Happens |
| --- | --- |
| Student Life | YGN + MDY students answer “What is STIMU really like?” |
| Try Your Program | Short, accessible Business / Computing-AI / Engineering / Built Environment / Health activities. |
| Degree → Career | Show each program’s skills, careers, progression and realistic future pathways. |
| Explore → Apply → Join | Program fit, eligibility, application, scholarship/fees and registration next step. |

# 7. Parent Conversion Track | မိဘများအတွက် သီးခြား Journey

Parent session should be practical, brief and reassuring: STIMU credibility → academic quality → degree pathway → student support → employability → fees/value → scholarship → next step. Senior management and faculty should meet parents directly. အရှည်ကြီး presentation မလုပ်ဘဲ မိဘများ မေးလိုသည့်အချက်များကို ရှင်းလင်းပြီး ယုံကြည်မှုတည်ဆောက်ရန်။

# 8. Conversion Funnel & Ownership

INVITE → ATTEND → EXPERIENCE → TRUST → CONSULT → APPLY → REGISTER

| Owner | Accountability |
| --- | --- |
| MDY Head / Event Conversion Lead | Overall delivery + final enrolment outcome |
| Digital Marketing | Qualified registrations for event + attendance |
| Admissions | Lead qualification, application and registration |
| Faculty | Academic credibility + program-fit consultation |
| YGN Students | Aspiration, peer trust, One STIMU proof |
| MDY Students | Local credibility, belonging, authentic experience |
| Senior Management | Parent confidence + intervention for high-value undecided prospects |
| Finance/Admin | Controlled budget, transport, logistics, event readiness |

# 9. Pre-Event Execution | T−21 to T−1

• T−21 to T−14: Build prospect list from existing enquiries, schools, student referrals and digital leads. Every invite should be tagged by program interest and lead temperature.

• T−14 to T−7: Confirm YGN/MDY ambassadors; brief them on authentic peer engagement. Launch student-story content and direct parent invitations.

• T−7 to T−2: Admissions calls all registered prospects; confirm parent attendance; prioritize hot/warm prospects; prepare faculty matching.

• T−1: Final conversion list prepared: who is coming, what they want, who will speak to them, and what likely objection must be resolved.

# 10. Event-Day Lead Control

Every prospect must be tracked: Name → School → Source → Program interest → Parent attended? → Hot/Warm/Cold → Objection → Application status → Next action → Owner.

| Lead | Immediate Action |
| --- | --- |
| HOT | Faculty/admissions + parent discussion → application/registration pathway before leaving. |
| WARM | Identify objection → match to student/faculty/management → book follow-up within 48 hours. |
| COLD | Capture interest accurately → nurture content/event → scheduled admissions follow-up. |

# 11. Mandatory 7-Day Closing Sprint

| Timing | Action |
| --- | --- |
| Same day | Thank-you + clear application/next-step message. |
| 0–24 hrs | Admissions personally contacts every HOT prospect. |
| 24–72 hrs | Push applications; faculty follows academically undecided prospects. |
| Day 3–5 | Parent calls / family consultation for decision-dependent cases. |
| Day 5–7 | Management reviews all remaining high-value prospects; targeted intervention. |
| Day 7 | Board conversion report submitted. |

# 12. Budget Approval Principle

Approve a controlled conversion budget, not an open-ended event budget. Budget lines may include YGN student transport/accommodation, digital promotion, refreshments, event materials, student activities and essential campus presentation.

Board financial test: Event Cost ÷ Confirmed Registrations = Cost per Acquisition (CPA); compare CPA with first-year tuition revenue and normal recruitment acquisition cost.

# 13. Board Approval Conditions

1. Event is managed as a conversion project with a 15–20 registration outcome.

2. Minimum 80 prospective student attendees targeted, with parents deliberately invited.

3. YGN + MDY student-to-student interaction remains the signature component.

4. Formal speeches are kept short; most time is spent on experience, conversation and consultation.

5. A mandatory 7-day post-event closing sprint is owned by Admissions and MDY leadership.

6. Day-7 report shows Attendance → Qualified Leads → Applications → Registrations → CPA → Revenue Pipeline.

# Board Recommendation | အတည်ပြုရန် အကြံပြုချက်

RECOMMEND: APPROVE

Rationale: The Open House creates a concentrated conversion environment combining peer social proof, One STIMU identity, parent confidence, academic experience and immediate admissions closing. Event အောင်မြင်မှုကို လူဘယ်လောက်လာသည်ဖြင့် မတိုင်းတာဘဲ October intake အတွက် ဘယ်လောက် application နှင့် confirmed registration ပြောင်းနိုင်သည်ကို အဓိက KPI အဖြစ် သတ်မှတ်ရမည်။